## Sheet1
Function | Status | Plot Compatible | Notes
scarloc | Done | n/a
coreloc | Discard | n/a
ll2ps | Done | n/a
ps211 | Done | n/a |  | antmap, bedmap2, pcolorm for testing
psgrid | Done
uv2vxvy | Done | n/a | I also have this done but looks similar so not adding it in (Alisha) | needs antmap, pcolorm, bedmap2, quivermc, quiver for testing
vxvy2uv | Done | n/a
inpsquad | Done | n/a
pathdist | Done | n/a | does not support rhumb line distances, as the MATLAB function does
pathdistps | Done?? | n/a | in pypmt… had difficulty checking the test cases in matlab | bedmap2 for testing
psdistortion | Done | n/a |  | pcolorps, graticuleps for testing
pspath | Done?? | n/a | same issue as pathdistps | plotps for testing
pathcrossingps71 | Done | n/a | needs clip_outliers and InterX to run (included in PyPMT) | needs mapzoomps to test
crossovers
freeboard2thickness | Done | n/a
thickness2freeboard | Done | n/a |  | needs patch, uistack for testing
base2freeboard | Done | n/a
ice_profile_smoother | On hold |  | bedmachine tests, need pathdistps for testing
peclet | On hold
gridded_flux | Debug | need its_live and measures velocity data first | Need help… can't figure it out (Blake) | bedmachine test (needs interpolation functions we don't have)
mapzoomps | Started |  | Needs scarlabel and scalebarps
plotps | Done | yes |  | bedmap testing
plot3ps | Done | yes
pcolorps | Done | yes | takes like 7-8 minutes though (for complete bedmachine data)
surfps | Done | n/a
patchps | Done |  |  | works with antbounds
scatterps | Done | yes
contourps | Done
contourfps | Done
quiverps | Done | unknown
textps | Done | yes
graticuleps | Debug | looks right??
circleps | Done | yes
geoquadps | Done | yes
scalebarps
scarlabel | Done | yes
colorbarps | Done
shadem | delay
coord |  | interactive (mouse clicks)
clickz | having trouble with interactive functions
inset_unproj |  | think it makes more sense to have mapzoom first
mapzoom | delay
corelabel | Discard
scarclick
scalebar | 90% done |  | Debugging issues with scalebar going off the plot
quivermc | Done | unknown
islatlon | Done | n/a
ps2wkt | Done | n/a
find2drange | Done | n/a
C2xyz | Done
antbounds | Done | yes
greenland_bounds | In progress | yes
clip_outliers (subfunction) | Done | n/a
bedmachine_data | In progress | n/a